## MSS res
NO | update | NAME | KW | PH | BANK | LOCATION | DISCOM | K.NO | MOBILE | GMAIL | GPS / LINK | QUATATION IN BANK | FINAL DEAL with client | LOAN | Cash | File login | SUBSIDY | BANK FILE/CASH | WORK STATUS | DISCOM WORK | PAYMENT STATUS | 1ST INSTALLMENT | 2ND INATALLMENT | CASH TO MSS | Bank due | CASH DUE FROM CLIENT | NET DUE TO MSS | TOTAL Payment recieved | REMARK
1 | CANCEL | GOPAL PARJAPT updated | 10KW | 3PH |  | DADI KA FATAK | SHALIMAR CHORHA | 210475041693 | 8949518513 | GOPAL1979PRAJAPAT1721@GMAIL.COM | 26°58'10.1"N 75°45'02.5"E | 389000 | 389000 | 0 |  | File login | Center (78K) | CASH FILE | Project On Hold | Pending | Payment Not Received Yet | [5 empty] | 0 | 0
2 | CIVIL DOWN | LAXMINARAYAN YADAV | 3KW | 1PH |  | KARANSAR | JOBNER | 211543027987 | 9667778772 | MUKESHSAAP143@GMAIL.COM |  | 200000 | 180000 | 180000 |  | File login | Both (78 + 17) | Loan Rejected | Project On Hold | Pending | Payment Not Received Yet | [5 empty] | 0 | 0
3 | REJECT |  | 5kw | [5 empty] | 8619394617 | anandyadav0707@gmail.com | 26°57'07.7"N 75°43'06.3"E | 225000 | 280000 |  | 280000 | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet |  |  |  | 0 | 280000 | 280000 | 0
4 | LOGIN | SAPNA KANWAR | 3kw | 1PH |  | MACHVA | KALWAR | 211525046382 | 7793053843 | SAPNAKANWAR6378@GMAIL.COM | 26°56'42.3"N 75°39'09.5"E | 206000 | 185000 |  |  | File login | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
5 | BILL ME CORRECTION | SHRAWAN KUMAR | 5KW | 1PH |  | KARANSAR | JOBNER | 211543005127 | 9462077152 | manish17082008@gimal.com | 27°05'34.6"N 75°28'42.5"E | 225000 | 270000 |  | 270000 | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet |  |  |  | 0 | 270000 | 270000 | 0
6 | CIVIL DOWN | FULCHAND | 3KW | 1PH | BOI | MUNDIYAGARH | RENWAL | 211544015872 | 9950016481 | CHAMANCHOUDHAARY0000@GMAIL.COM | 27°06'48.2"N 75°23'59.5"E | 211000 | 190000 | 190000 | 0 | File login | Center (78K) | File into bank | Project On Hold | Pending | Payment Not Received Yet | 0 | 0 | 0 | 190000 | 0 | 190000 | 0
7 | DOCUMENTS PENDING | GANPAT SINGH | 5KW | 1PH |  |  | JOBNER | 211543007710 | 9982563365 | Singhganpat315@gmail.com |  |  |  |  | 0 | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet |  |  |  | 0 | 0 | 0 | 0
8 | LOAN APPLY | BASU KANWAR | 3KW | 1PH | SBI | KHIJURIYA | JOBNER | 211543031209 | 9799060293 | tejsingh5664@gmail.com | 27°05'34.1"N 75°28'41.9"E | 212000 | 190000 | 190000 | 0 | File login | Center (78K) | Loan Rejected | Project On Hold | Pending | Payment Not Received Yet | 0 | 0 | 0 | 190000 | 0 | 190000 | 0
9 | LOAN REJECT CIVIL 630 | GOPAL LAL KUMAWAT(NON DCR) | 10KW | 3PH |  | SIRSI | BINAYAKA | 210416018682 | 9799390746 | PRADHUMAN038@GMAIL.COM | 26°54'32.7"N 75°40'45.6"E |  | 400000 |  | 400000 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 0 | 400000 | 400000 | 0
1 | COMPLETED | RAMGOPAL | 3KW | 1PH |  | KHERI MILK | JOBNER | 211543006721 | 9660574963 | RADHESYAMYADAV269@GMAIL.COM |  | 178000 | 178000 | 0 | 178000 | COMPLET | Both (78 + 17) | CASH FILE | I&C Completed | Subsidy granted | Cash To Mahi | 0 | 0 | 178000 | 0 | 0 | 0 | 178000
2 | COMPLETED | BHAGWANI DEVI | 4KW | 1PH | SBI | GOVINDPURA | GOVINDPURA | 210474069287 | 9079641962 | Rajkumarkumawat141@gmail.com | 26.952214, 75.697396 | 215000 | 215000 | 193000 | 22000 | COMPLET | Center (78K) | Loan approved | I&C Completed | Subsidy granted | 2ns Installment Received | 135000 | 58000 | 22000 | 0 | 0 | 0 | 215000
3 | COMPLETED 12K CHEAQUE LENA H WELDING ,SPRY OR SUPPORT PENDING | MAHENDRA KUMAR JANGID | 3+5KW | 3PH | SBI | JHOTWARA | nala powehouse | 210412021477 | 9928419414 | mkjangid97@gmail.com | 26°56'14.2"N 75°44'44.9"E | 390000 | 390000 | 200000 | 190000 | COMPLET | Both (78 + 17) | Loan approved | I&C Completed | Subsidy granted | Payment Due | 140000 | 60000 | 178000 | 0 | 12000 | 12000 | 378000 | 12K KA CHEAQUE LENA H
4 | COMPLETED | RAM CHANDRA MEENA | 3KW | 1PH |  | MURLIPURA | MURLIPURA | 210473009614 | 8005545213 | VED9NADHI93@GMAIL.COM | 26°58'37.1"N 75°46'10.6"E | 180000 | 171000 | 0 | 171000 | COMPLET | Both (78 + 17) | CASH FILE | I&C Completed | Subsidy granted | Cash To Mahi | 0 | 0 | 171000 | 0 | 0 | 0 | 171000
5 | COMPLETED | SHIPU KUMARI | 3KW | 1PH |  | HATHOJ | HATHOJ | 211529037288 | 8441010572 | abhi64singh@gmail.com | 26°57'41.2"N 75°41'24.3"E | 180000 | 180000 | 0 | 180000 | COMPLET | Center (78K) | CASH FILE | I&C Completed | Subsidy granted | Cash To Mahi | 0 | 0 | 180000 | 0 | 0 | 0 | 180000
6 | COMPLETED | KAILASH CHAND KUMAWAT | 5KW | 1PH |  | HATHOJ | HATHOJ | 211529031447 | 9829488108 | kkumawat606@gmail.com | 26°57'18.3"N 75°39'55.2"E | 250000 | 250000 | 0 | 250000 | COMPLET | Center (78K) | CASH FILE | I&C Completed | Subsidy granted | Cash To Mahi | 0 | 0 | 250000 | 0 | 0 | 0 | 250000
7 | COMPLETED | ghanshayam pareek | 5kw | 1PH |  | GOVINDPURA | HATHOJ | 211529025030 | 9414717688 | pareeksunil44@gmail.com | 26°57'40.9"N 75°42'29.7"E | 250000 | 250000 | 0 | 250000 | COMPLET | Center (78K) | CASH FILE | I&C Completed | Subsidy granted | Payment Due | 0 | 0 | 245000 | 0 | 5000 | 5000 | 245000 | 5k clinte nhi dega
8 | COMPLETED | GANGA RAM RAIGAR | 3KW | 1PH | SBI | KHIRVA | JOBNER | 211543011297 | 9983887214 | Dsdewat@gmail.com | 27°03'12.5"N 75°24'45.5"E | 195000 | 175000 | 175000 | 0 | COMPLET | Center (78K) | Loan approved | I&C Completed | Subsidy granted | 2ns Installment Received | 122500 | 52500 | 0 | 0 | 0 | 0 | 175000
9 | SUBSIDY PENDING | PRADEEP SINGH | 3KW | 1PH |  | RAMJIPURA KALA | JOBNER | 211543033384 | 6367129868 | PSSHEKHAWAT6376@GMAIL.COM | 27°05'32.2"N 75°23'16.6"E | 180000 | 180000 | 0 | 180000 | COMPLET | Center (78K) | CASH FILE | I&C Completed | Subsidy apply with site photo | Cash To Mahi | 0 | 0 | 180000 | 0 | 0 | 0 | 180000
10 | WORK ON HOLD DUE TO PAYMENT ISSUE | VIJAY KUMAR | 5KW | 3PH | SBI | AMBER | AMBER | 210454061878 | 9413335394 | vipcomputersjpr@gmail.com | Hotel Kanak Palace and Restro | 225000 | 250000 | 200000 | 50000 | COMPLET | Center (78K) | Loan approved | I&C Completed | Meter & File submit DISCOM | 1st Installment Received | 140000 | 0 | 0 | 60000 | 50000 | 110000 | 140000
11 | COMPLETED | AJAY SHARMA | 5KW | 3PH | SBI | AMBER | AMBER | 210454061879 | 9414072658 | ajaysharma.as3677@gmail.com | Hotel Kanak Palace and Restro | 225000 | 250000 | 200000 | 50000 | COMPLET | Center (78K) | Loan approved | I&C Completed | Subsidy granted | Payment Due | 140000 | 60000 | 60000 | 0 | -10000 | -10000 | 260000
12 | SUBSIDY PENDING | BADRI NARAYAN | 5KW | 1PH | PNB | BHIASLANA | RENWAL | 211544017315 | 9929814037 | HEMRAJCHOUDHARY1204@GMAIL.COM | 27°02'52.0"N 75°17'37.0"E | 225000 | 280000 | 200000 | 80000 | COMPLET | Center (78K) | Loan approved | I&C Completed | Subsidy apply with site photo | 2ns Installment Received | 120000 | 80000 | 80000 | 0 | 0 | 0 | 280000
13 | COMPLETED 6000 LENA H | MANISH DADHICH | 6KW | 3PH |  | PARTAP ENCLACE | NRI | 211482008587 | 8114487781 | Manish.dadhich@ gmail.com | 26°48'50.4"N 75°50'47.2"E | 310000 | 310000 | 0 | 310000 | COMPLET | Center (78K) | CASH FILE | I&C Completed | Subsidy granted | Payment Due | 0 | 0 | 304000 | 0 | 6000 | 6000 | 304000
14 | COMPLETE 2K nhi dege | SITARAM YADAV | 3KW | 1PH |  | GOVINDPURA | JHOTWARA | 210474051333 | 9587335297 | SITARAMYADAV1964@GMAIL.COM | 26°57'11.1"N 75°41'44.3"E | 180000 | 180000 | 0 | 180000 | COMPLET | Center (78K) | CASH FILE | I&C Completed | Subsidy granted | Payment Due | 0 | 0 | 178000 | 0 | 2000 | 2000 | 178000 | 2000 CLINT NHI DEGA
15 | COMLETED | ANANDI LAL KUMAWAT | 3KW | 1PH | BOI | RENWAL | RENWAL | 211544020862 | 9667029477 | SOHANKUMAWAT310@GMAIL.COM | 27°10'27.5"N 75°21'58.2"E | 200000 | 180000 | 180000 | 0 | COMPLET | Both (78 + 17) | Loan approved | I&C Completed | Subsidy granted | 2ns Installment Received | 180000 | 0 | 0 | 0 | 0 | 0 | 180000
16 | SUBSIDY,2ND PAYMENT PENDING | ASHOK NARWAL | 4KW | 1PH | CBOI | PANCHYAWALA | BINAYAKA | 210416041093 | 9929294507 | ASHOKNARWAL73@ICLOUD.COM | 26°55'05.9"N 75°42'51.1"E | 225000 | 225000 | 200000 | 25000 | COMPLET | Center (78K) | Loan approved | I&C Completed | Subsidy apply with site photo | 1st Installment Received | 165000 | 0 | 0 | 35000 | 25000 | 60000 | 165000
17 | SUBSIDY,SECOND PAYMENT PENDING | GULAB SHARAM | 3KW | 1PH | SBI | NIWARU | HATHOJ | 211529001130 | 9314001794 | raj.khandal5422@gmail.com | 26°57'45.1"N 75°43'07.9"E | 200000 | 180000 | 180000 | 0 | COMPLET | Both (78 + 17) | Loan approved | I&C Completed | Net Metering | 1st Installment Received | 126000 | 0 | 0 | 54000 | 0 | 54000 | 126000
18 | SUBSIDY PENDING | choti devi | 3kw | 1ph |  | KRANASAR | JOBNER | 211543010351 | 9799211493 | SPK9799211493@GMAIL.COM | 27°05'40.8"N 75°26'45.7"E | 175000 | 175000 | 0 | 175000 | COMPLET | Both (78 + 17) | CASH FILE | I&C Completed | Net Metering | Payment Due | 0 | 0 | 25000 | 0 | 150000 | 150000 | 25000
19 | SUBSIDY PENDING | MUNNI DEVI | 3KW | 1PH | SBI | KARANSAR | JOBNER | 211543030612 | 8769332218 | MAHAVEER8769@GMAIL.COM | https://maps.app.goo.gl/hLD6XMWq8Piqmn7B9?g_st=aw | 175000 | 175000 | 0 | 175000 | COMPLET | Both (78 + 17) | CASH FILE | I&C Completed | Net Metering | Payment Due | 0 | 0 | 150000 | 0 | 25000 | 25000 | 150000
20 | METER, SUBSIDY PENDING | BABU LAL KUMHAR | 3kw | 1ph |  | CHATARPURA | SANGANER RURAL | 211584071911 | 9244122178 | krishan.nitrr@gmail.com | 26°49'44.2"N 75°53'19.1"E | 175000 | 175000 | 0 | 175000 | COMPLET | Center (78K) | CASH FILE | I&C Completed | Meter & File submit DISCOM | Payment Due | 0 | 0 | 175000 | 0 | 0 | 0 | 175000
21 | METER, SUBSIDY PENDING | HANUMAN SAHAI SHARMA | 5KW | 1PH | PNB | SARNA DOONGAR | ROJDA | 211521017893 | 8233515414 | R.sharma5414@जीमेल.com | 26°59'55.1"N 75°41'59.0"E | 225000 | 240000 | 200000 | 40000 | COMPLET | Both (78 + 17) | Loan approved | I&C Completed | Meter & File submit DISCOM | 1st Installment Received | 132000 | 0 | 25000 | 68000 | 15000 | 83000 | 157000
22 | METER, SUBSIDY PENDING | NIRMALA KUMAWAT | 8KW | 3PH | SBI | GOVINDPURA | JHOTWARA | 210474001512 | 9829083182 | MAHESHKUMAWAT440@GMAIL.COM | 26°57'07.8"N 75°42'22.6"E | 225000 | 400000 | 200000 | 200000 | COMPLET | Center (78K) | Loan approved | I&C Completed | Meter & File submit DISCOM | 1st Installment Received | 140000 | 0 | 100000 | 60000 | 100000 | 160000 | 240000
23 | METER, SUBSIDY PENDING | ANKIT AGARWAL | 5KW | 1PH | SBI | JHOTWARA | JHOTWARA | 210474076481 | 9001108083 | AANKIT925@GMAIL.COM | 26°56'44.1"N 75°42'29.3"E | 225000 | 240000 | 200000 | 40000 | COMPLET | Center (78K) | Loan approved | I&C Completed | Meter & File submit DISCOM | 1st Installment Received | 140000 |  | 20000 | 60000 | 20000 | 80000 | 160000 | 20K SUBSIDY PE DEGA
24 | FILE LOGIN mk se update lena h | RAMA SHARMA[yesh bhai ki file n] | 3KW | 1PH |  | HARANATH PURA | JHOTWARA | 210474035805 | 8005634915 | kumaryash1910@gmail.com | https://goo.gl/maps/W5eCVVrmGxMHixis6?g_st=aw | 178000 | 178000 | 0 | 178000 | File login | Both (78 + 17) | CASH FILE | Work Not Started Yet | Meter & File submit DISCOM | Payment Not Received Yet | 0 | 0 | 0 | 0 | 178000 | 178000 | 0
25 | BANK SE CALL AA GYA H PR BANK NHI JAA RHE H | URMILA KANWAR | 5KW | 1PH | BOB | NIWARU | HATOJ | 211529019778 | 9680503384 | Sss9680503384@gmail.com | 26°58'56.3"N 75°43'13.3"E | 255000 | 255000 | 200000 | 55000 | File login | Both (78 + 17) | File into bank | Work Not Started Yet | Pending | Payment Not Received Yet | 0 | 0 | 0 | 200000 | 55000 | 255000 | 0
26 | STRUCTURE WORK ONLY | ARCHANA | 5KW | 3PH | SBI | SIRSI | BINAYAKA | 210416044512 | 7014841157 | KSUNAND@gmail.com | 26°55'21.9"N 75°38'14.6"E | 260000 | 260000 | 200000 | 60000 | File login | Center (78K) | Loan approved | Structure Work | Meter & File submit DISCOM | 1st Installment Received | 140000 | 0 | 0 | 60000 | 60000 | 120000 | 140000
27 | FILE LOGIN/NEW PASSBOOK NHI AAYI CIVIL DOWN H SAYAD CASE ME HO | ARJUN LAL JAT | 5KW | 1PH |  | KALAKH | JOBNER | 211543012496 | 9772332271 | deepakchoudhary3133@gmail.com | 27°00'19.7"N 75°28'02.9"E |  |  |  |  | File login | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet | 0 | 0 | 0 | 0 | 0 | 0 | 0
28 | CONFIRM KRNA H | GOPAL LAL CHOUDHARY | 3+5KW | 3PH |  | SHIKARPURA | SHIKARPURA | 211467014489 | 9929885367 | gopal9929885367@gmail.com | https://maps.app.goo.gl/L8mwF8NwZcfiQYPT8?g_st=aw | 225000 | 350000 | 200000 | 150000 | Doc Recieved | Both (78 + 17) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet | 0 | 0 | 0 | 200000 | 150000 | 350000 | 0
29 | BILL NAME CHANGE | SARVESH KUMAR SHARMA | 5KW | 3PH |  | KHATIPURA | NALA POWER | 210412024739 | 8005772304 | rjharshsharma014@gmail.com |  |  |  |  | 0 | File login | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet | 0 | 0 | 0 | 0 | 0 | 0 | 0 | DEMAND JAAMA NHI KRVA RHA H
30 | PASSBOOK PENDING HOLD PR RKHNA ABHI | SANTRA | 5KW | 1PH |  |  | BAGRU | 211534070409 | 9887624524 | raghu24524@gmail.com | 26°51'00.5"N 75°36'15.3"E | 225000 | 280000 | 200000 | 80000 | File login | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet | 0 | 0 | 0 | 200000 | 80000 | 280000 | 0 | PASSBOOK SEND NHI KR RHA H
31 | CLIENT NE LOAN REJECT KRVADIYA | NARENDRA SINGH | 3kw | 1PH | RGB | PINDOLAI | KALWAR | 211525056995 | 7062831960 | narendrasinghh37@gmail.com | 26°56'42.2"N 75°38'59.3"E | 195000 | 175000 | 175000 | 0 | File login | Center (78K) | Loan Rejected | Work Not Started Yet | Pending | Payment Not Received Yet | 0 | 0 | 0 | 175000 | 0 | 175000 | 0
32 | DOCUMENTS PENDING GROUP ME LOCATION KE ALVO KOI INFORMANTION NHI H |  | 5KW | 3PH | [6 empty] | 26°58'26.1"N 75°44'46.2"E | 225000 | 300000 | 200000 | 100000 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 200000 | 100000 | 300000 | 0
33 | DOCUMENTS PENDING CALL PICKUP NHI KR RHE H |  | 3kw | 1ph |  | MACHVA |  |  | 9314777776 |  | 26°57'46.2"N 75°39'06.1"E |  | 190000 |  | 190000 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 0 | 190000 | 190000 | 0
34 | PAN UPDATE HOGA CALL PICKUP NHI KR RHE H | RAMLAL KUMAWAT | 6KW | 3PH | SBI | HATHOJ | HATHOJ | 211529036131 | 7073654309 | RM7073654309@GMAIL.COM | 26°58'20.4"N 75°40'58.9"E | 225000 | 320000 | 200000 | 120000 | File login | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 200000 | 120000 | 320000 | 0
35 | LOAN APPLY | KAMAL KISHORE KUMAWAT | 3KW | 1PH | BOB | KALADERA | KALADERA | 210516017535 | 8385001747 | KK5795419@GMAIL.COM | https://maps.app.goo.gl/qpGz63SHLsPozd789?g_st=aw | 195000 | 175000 | 175000 | 0 | File login | Both (78 + 17) | File into bank | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 175000 | 0 | 175000 | 0
36 | LOAN APPLY | RAMDHAN BUNKAR | 3KW | 1PH | UNION | TANTYAWAS | JAITPURA | 211527026825 | 9929995027 | ramdhanbayala@gmail.com | 27°04'55.8"N 75°40'18.9"E | 195000 | 175000 |  | 175000 | File login | Center (78K) | File into bank | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 0 | 175000 | 175000 | 0
37 | ADHAR CARD SUSPENDED H | KISTURI DEVI | 3KW | 1PH | SBI | RAMJIPURA | JOBNER | 211543022424 | 9636402416 | CMDHAYAL14@GMAIL.COM | 27°06'15.2"N 75°24'06.2"E | 200000 | 180000 | 180000 | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 180000 | 0 | 180000 | 0
38 | LOAN REAPPLY HOGA | JAGDISH PRASAD KUMAWAT | 3KW | 1PH | SBI | HIGONIYA | JOBNER | 211543028689 | 7568166860 | kumardkumawat2000@gmail.com | 27°02'08.1"N 75°27'33.0"E | 195000 | 175000 | 175000 | 0 | File login | Center (78K) | File into bank | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 175000 | 0 | 175000 | 0
39 | PRIVATE BANK SE LOAN | narayan lal kumawat(non dcr) | 10kw | 3ph |  | JOBNER | JOBNER | 211543015954 | 9414820656 | naryanlal1999@gmail.com | 26°59'01.3"N 75°22'58.9"E |  | 400000 |  | 400000 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 0 | 400000 | 400000 | 0
40 | LOAN APPLY | BHERU LAL JAT | 5KW | 1PH | SBI | MACHVA | KALWAR | 211525056339 | 9829652586 | bharulaljat@gmail.com | 26°57'26.3"N 75°38'18.5"E | 245000 | 245000 |  | 245000 | File login | Center (78K) | File into bank | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 0 | 245000 | 245000 | 0
41 | WORK START KRNA H | SANDEEP SINGH RAJAWAT | 5kw | 1PH | SBI | SHIKARPURA | SHIKARPURA | 211467015514 | 9602597714 | singh.sandeep328@gmail.com | 26°45'48.4"N 75°48'04.5"E | 265000 | 265000 | 200000 | 65000 | File login | Center (78K) | Loan approved | Structure Work | Meter & File submit DISCOM | 1st Installment Received | 140000 |  |  | 60000 | 65000 | 125000 | 140000
42 | NEW CONNECTION FILE LGA DI H | KAILASHI DEVI | 5KW | 1PH |  |  | NALA POWER | 210412001213 |  |  | 26°54'24.0"N 75°46'23.1"E | 235000 | 235000 |  | 235000 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 0 | 235000 | 235000 | 0
43 | NEW CONNECTION FILE LGA DI H | SEEMA(NON DCR) | 10KW | 3PH |  |  | NALA POWER | 210412004241 | 9509280175 | DEEPAKJORIYA93@GMAIL.COM | 26°54'18.9"N 75°46'12.4"E | 350000 | 350000 |  | 350000 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 0 | 350000 | 350000 | 0
44 | LOAN APPLY ACCOUNT UPDATE HOGA | KAMLA DEVI KAJLA | 3kw | 1ph | SBI | hathoj | HATHOJ | 211529027784 | 9783503030 | maheshkajala@gmail.com | 26°57'28.2"N 75°39'59.2"E | 200000 | 180000 | 180000 | 0 | File login | Center (78K) | File prepare | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 180000 | 0 | 180000 | 0
45 | DOCUMENTS PENDING |  | 3KW | 1PH | [6 empty] | 26°49'36.0"N 75°46'25.7"E | 180000 | 180000 | 0 | 180000 | Doc Recieved | Center (78K) | CASH FILE | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 0 | 180000 | 180000 | 0
46 | LOAN APPLY | NANU RAM MEENA | 5KW | 1PH |  | JOBNER | JOBNER | 211543021862 | 9413969527 | Naren.jaif@gmail.com | 26°58'31.9"N 75°23'07.9"E | 200000 | 180000 | 180000 | 0 | File login | Center (78K) | File into bank | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 180000 | 0 | 180000 | 0
47 | HOLD | RAJU KUMAWAT | 3KW | 1PH |  |  |  | 110521002365 | 9413943652 | RAJUKUMAWAT652@GMAIL.COM | 27°18'48.3"N 75°09'20.7"E | 206000 | 185000 |  | 185000 | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet |  |  |  | 0 | 185000 | 185000 | 0
48 | PAN UPDATE HOGA | UMA | 3KW | 1PH | SBI | LALCHANDPURA | HATHOJ | 211529037099 | 7976921346 | Chandra1986satyamtvs@gmail.com | 26°59'08.6"N 75°41'07.6"E | 195000 | 175000 | 175000 | 0 | File login | Center (78K) | File into bank | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 175000 | 0 | 175000 | 0
49 | [14 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 0 | 0 | 0 | 0
50 | [14 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 0 | 0 | 0 | 0
[15 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 0 | 0 | 0 | 0
[15 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 0 | 0 | 0 | 0
[15 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 0 | 0 | 0 | 0
[15 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 0 | 0 | 0 | 0
[15 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 0 | 0 | 0 | 0
[15 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 0 | 0 | 0 | 0
[15 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 0 | 0 | 0 | 0

## SHRIPAL JI
| UPDATE | NAME | KW | PH | BANK | LOCATION | DISCOM | K.NO | MOBILE | GMAIL | GPS / LINK | QUATATION IN BANK | FINAL DEAL WITH CLIENT | DEAL WITH MSS | LOAN | CASH | FILE LOGIN | SUBSIDY | BANK FILE/CASH | WORK STATUS | DISCOM WORK | PAYMENT STATUS | 1ST INSTALLMENT | 2ND INATALLMENT | CASH TO MSS | PAYMENT WITH PARTNER | CASH DUE FROM CLIENT | BANK DUE | CASH DUE TO MSS | NET DUE TO MSS | TOTAL PAYMENT RECIVED | REMARK
1 | reject | GEETA DEVI | 3KW | 1PH |  | HATOJ | HATOJ | 211529035324 | 9887110287 | RAMKUMARGURJAR09@GMAIL.COM |  | 200000 | 180000 | 180000 | 180000 | 0 | File login | Center (78K) | File into bank | Project On Hold | Pending | Payment Not Received Yet |  |  |  |  | 0 | 180000 | 0 | 180000 | 0
2 | reject | DEVA RAM | 3KW | 1PH |  | PHULERA | SAMBHAR | 211541008105 | 7073082353 | DDNSPM.PR92@GMAIL.COM | 26°58'12.2"N 75°11'57.0"E | 200000 | 180000 | 180000 |  | 180000 | File login | Both (78 + 17) | Loan apply | Project On Hold | Pending | Payment Not Received Yet |  |  |  |  | 180000 | 0 | 180000 | 180000 | 0
3 | LOAN APPLY | SARJU KANWAR | 3KW | 1PH |  | HATHOJ | HATHOJ | 211529013655 | 8208276421 | singhrajpal955@gmail.com | 26°57'35.6"N 75°40'32.6"E | 200000 | 190000 | 190000 | 180000 | 10000 | File login | Both (78 + 17) | File into bank | Project On Hold | Pending | Payment Not Received Yet |  |  |  |  | 10000 | 180000 | 10000 | 190000 | 0
4 | BILL ME NAME TRANSFER HOLD | MAMTA | 3KW | 1PH |  | NIWARU | JHOTWARA |  | 9829636341 |  |  | 190000 | 190000 |  |  | 190000 | File login | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet |  |  |  |  | 190000 | 0 | 0 | 0 | 0
5 |  | UMED SINGH | [6 empty] | 8397838308 | [6 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet |  |  |  |  | 0 | 0 | 0 | 0 | 0
6 | CONFIRM NHI H ABHI | BHANWAR SINGH | 5KW | 1PH |  | NIWARU | SHALIMAR | 210475028311 | 9887184413 | surendrasingh.rajawat5@gmail.com | 26°57'14.9"N 75°43'48.1"E | 263000 | 263000 | 263000 | 200000 | 63000 | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet |  |  |  |  | 63000 | 200000 | 63000 | 263000 | 0
7 | LOGIN | KHANGA RAM | 3kw | 1ph | SBI | SIRSI ROAD | HATHOJ | 211529008855 | 8000495813 | daraml1986@gmail.com | 26°56'45.5"N 75°40'30.2"E | 200000 | 180000 | 180000 | 180000 | 0 | File login | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet |  |  |  |  | 0 | 180000 | 0 | 180000 | 0
8 | PRIVATE BANK SE LOAN | UMED SINGH |  |  |  |  | HATHOJ | 211529014006 | 9602961770 | UMEDTANWAR1078@GMAIL.COM |  |  | 220000 | 220000 |  | 220000 | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet |  |  |  |  | 220000 | 0 | 220000 | 220000 | 0
1 | COMPLETED ,8 K NHI DEGA | AJAPAL YADAV | 5KW | 3PH | SBI | GOVINDPURA | JHOTWARA | 210474048668 | 7610057089 | AJAYYADAV00393@GMAIL.COM | 26°57'11.1"N 75°41'44.3"E | 225000 | 260000 | 260000 | 200000 | 60000 | COMPLET | Both (78 + 17) | Loan approved | I&C Completed | Subsidy granted | Payment Due | 120000 | 80000 | 20000 | 32000 | 8000 | 0 | 40000 | 40000 | 252000 | 8K CLINT NHI DEGA
2 | COMPLETED | LADHU RAM GURJAR | 3KW | 1PH | SBI | HATHOJ | HATHOJ | 211529036714 | 9772603753 | jkjagdish13@gmail.com | 26°57'54.2"N 75°40'30.9"E | 200000 | 180000 | 180000 | 180000 | 0 | COMPLET | Center (78K) | Loan approved | I&C Completed | Subsidy granted | 2ns Installment Received | 125000 | 55000 |  |  | 0 | 0 | 0 | 0 | 180000
3 | COMPLETED | DURGA DEVI | 3+7KW | 3PH | SBI | NIWARU | SHALIMAR | 210475028681 | 9001392388 | ranveersinghjadoun1234@gmail.com | 26°57'35.4"N 75°43'48.4"E | 405000 | 400000 | 400000 | 200000 | 200000 | COMPLET | Center (78K) | Loan approved | I&C Completed | Subsidy granted | Payment Due | 140000 | 60000 | 198000 |  | 2000 | 0 | 2000 | 2000 | 398000 | PAYMENT CLEAR
4 | COMPLETED | BRIJ KISHOR RATHOR | 5KW | 3PH | SBI | HARNATHAPURA | JHOTWARA | 210474033438 | 9602394557 | Vishnurathore@gmail.com | 26°57'09.9"N 75°43'35.1"E | 225000 | 270000 | 270000 | 200000 | 70000 | COMPLET | Both (78 + 17) | Loan approved | I&C Completed | Subsidy granted | 2ns Installment Received | 140000 | 60000 | 70000 |  | 0 | 0 | 0 | 0 | 270000
5 | COMPLETED | MALIRAM RAHORIA | 3KW | 1PH | SBI | GOVINDPURA | JHOTWARA | 210474076189 | 9829594507 | srkumawat5768@gmail.com | 26°57'27.1"N 75°42'20.8"E | 200000 | 180000 | 180000 | 180000 | 0 | COMPLET | Both (78 + 17) | Loan approved | I&C Completed | Subsidy granted | 2ns Installment Received | 126000 | 54000 |  |  | 0 | 0 | 0 | 0 | 180000
6 | SUBSIDY PENDING | VIMLA DEVI | 3KW | 1PH | INDIAN BANK | HATHOJ | HATHOJ | 211529013585 | 9829367152 | rsg12116@gmail.com | 26°57'39.9"N 75°40'39.8"E | 200000 | 180000 | 180000 | 180000 | 0 | COMPLET | Both (78 + 17) | Loan approved | I&C Completed | Subsidy apply with site photo | 2ns Installment Received | 120000 | 60000 |  |  | 0 | 0 | 0 | 0 | 180000
7 | COMPLETED | MANOJ KAWNAR | 3KW | 1PH | SBI | HATHOJ | HATHOJ | 211529013405 | 9166735441 | vs7545104@GMAIL.COM | 26°58'01.6"N 75°40'18.4"E | 200000 | 180000 | 180000 | 180000 | 0 | COMPLET | Both (78 + 17) | Loan approved | I&C Completed | Subsidy granted | 2ns Installment Received | 126000 | 54000 |  |  | 0 | 0 | 0 | 0 | 180000
8 | completed | RAJU DEVI | 5KW | 1PH | UNION | NIWARU | JHOTWARA | 210474033378 | 9509510835 | sanjaysaini95095@gmail.com | 26°57'11.2"N 75°43'33.6"E | 225000 | 250000 | 250000 | 200000 | 50000 | COMPLET | Both (78 + 17) | Loan approved | I&C Completed | Subsidy granted | 2ns Installment Received | 100000 | 100000 | 40000 | 10000 | 0 | 0 | 10000 | 10000 | 250000 | 10K SHRIPAL JI KE PASS
9 | SUBSIDY PENDING | NEMICHAND KUMAWAT | 3KW | 1PH | SBI | DADI KA PATHK | SHALIMAR | 210475007020 | 7229912623 | vishnukumawat2121@gmail.com | 26°58'26.3"N 75°44'54.5"E | 200000 | 180000 | 180000 | 180000 | 0 | COMPLET | Center (78K) | Loan approved | I&C Completed | Subsidy apply with site photo | 2ns Installment Received | 125000 | 55000 |  |  | 0 | 0 | 0 | 0 | 180000
10 | SUBSIDY PENDING | ASHOK | 3KW | 1PH | BOB | HATHOJ | HATHOJ | 211529029681 | 9950690539 | ASHOK9950690539@GMAIL.COM | 26°58'04.7"N 75°40'33.3"E | 200000 | 180000 | 180000 | 180000 | 0 | COMPLET | Both (78 + 17) | Loan approved | I&C Completed | Net Metering | 2ns Installment Received | 126000 | 54000 |  |  | 0 | 0 | 0 | 0 | 180000
11 | METER,SUBSIDY PENDING | SHANU SHARMA | 3kw | 1ph | SBI | HATHOJ | HATHOJ | 211529033103 | 8107247277 | vijaykhandal7@gmail.com | 26°56'57.3"N 75°41'12.0"E | 212000 | 190000 | 190000 | 190000 | 0 | COMPLET | Center (78K) | Loan approved | I&C Completed | Meter & File submit DISCOM | 1st Installment Received | 133000 |  |  |  | 0 | 57000 | 0 | 57000 | 133000
12 | SUBSIDY PENDING | SHAMBHU DAYAL | 5KW | 1PH | BOB | JHOTWARA | JHOTWARA | 210474007973 | 9785103050 | Sainshambhu1971@gmail.com | 26°56'33.8"N 75°43'59.0"E | 225000 | 270000 | 270000 | 200000 | 70000 | COMPLET | Both (78 + 17) | Loan approved | I&C Completed | Net Metering | 1st Installment Received | 140000 |  |  |  | 70000 | 60000 | 70000 | 130000 | 140000
13 | METER,SUBSIDY PENDING | MAHENDER SINGH SHEKHAWAT | 5+6KW | 3PH |  | NIWARU | JHOTWARA | 210474033427 | 8972238334 | shailendarshekhawat2011@gmail.com | 26°57'11.9"N 75°43'36.0"E | 290000 | 290000 | 290000 | 0 | 290000 | COMPLET | Both (78 + 17) | CASH FILE | I&C Completed | Meter & File submit DISCOM | Payment Due |  |  | 200000 |  | 90000 | 0 | 90000 | 90000 | 200000
14 | METER,SUBSIDY PENDING | RADHA VALLABH PARASHAR | 6KW | 3PH | INDIAN | HATHOJ | HATHOJ | 211529006407 | 9314504223 | RADHAVALLABH1969@GMAIL.COM | 26°57'32.0"N 75°41'14.0"E | 320000 | 320000 | 320000 | 200000 | 120000 | COMPLET | Center (78K) | Loan approved | I&C Completed | Meter & File submit DISCOM | Payment Due |  |  | 100000 |  | 20000 | 200000 | 20000 | 220000 | 100000
15 | LOAN APPLY | SANJAY SAINI | 5KW | 1PH | MAHARASTAR | GOVINDPURA | HATHOJ | 211529024941 | 9667667666 | Sanjaysaini6221@gmail.com | 26°57'41.4"N 75°42'23.7"E | 250000 | 250000 | 250000 | 200000 | 50000 | File login | Center (78K) | File into bank | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 50000 | 200000 | 50000 | 250000 | 0
16 | loan reapply loga | HARIRAM VERMA | 5KW | 1PH | SBI | NIWARU | HATHOJ | 211529000317 | 9549217713 | VRAJ69606@GMAIL.COM | 26°57'55.5"N 75°43'06.6"E | 225000 | 250000 | 250000 | 200000 | 50000 | File login | Center (78K) | File into bank | Work Not Started Yet | Meter & File submit DISCOM | Payment Not Received Yet |  |  |  |  | 50000 | 200000 | 50000 | 250000 | 0
17 | LOAN APPLY | SUSHIL AGRAWAL | 5KW | 3PH | CANARA | MURLIPURA | VIDYADHAR | 210472044820 | 8209885400 | pariagrawal388@gmail.com | 26°58'03.7"N 75°45'52.8"E | 225000 | 275000 | 275000 | 200000 | 75000 | File login | Center (78K) | File into bank | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 75000 | 200000 | 75000 | 275000 | 0
18 | WORK START KRNA | PEERDAN SINGH | 3KW | 1PH | SBI | NIWARU | Shalimar Choraha | 210475023882 | 8947883394 | SHYAM.IT.PROFESSIONAL@GMAIL.COM | 26°57'58.6"N 75°43'56.0"E | 200000 | 180000 | 180000 | 180000 | 0 | File login | Center (78K) | Loan approved | Work Not Started Yet | Pending | 1st Installment Received | 126000 |  |  |  | 0 | 54000 | 0 | 54000 | 126000
19 | WIRING & INVERTER PENDING | MANJU DEVI | 3kw | 1ph | SBI | MANCHWA | KALWAR | 211525057547 | 9929272613 | KARANKUMAWAT981@GMAIL.COM | 26°57'06.1"N 75°39'08.5"E | 200000 | 180000 | 180000 | 180000 | 0 | File login | Center (78K) | Loan approved | Inverter pending | Meter & File submit DISCOM | 1st Installment Received | 126000 |  |  |  | 0 | 54000 | 0 | 54000 | 126000
20 | LOAN REJECT | GAJENDRA SINGH DIDAL | 3KW | 1PH |  | KISHORPURA | HATHOJ | 211529030154 | 9509093546 | gaju950909@gmail.com | 26°57'14.7"N 75°40'11.9"E | 200000 | 185000 | 185000 | 180000 | 5000 | File login | Center (78K) | File into bank | Work Not Started Yet | Meter & File submit DISCOM | Payment Not Received Yet |  |  |  |  | 5000 | 180000 | 5000 | 185000 | 0
21 | K NO. NHI AAYE ABHI TK | [7 empty] | 9529657002 | [6 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 0 | 0 | 0 | 0
22 | ACCOUNT OPEN HOGA | KAJAL MEENA | 3+5KW | 3PH | SBI | HATHOJ | KALWAR | 211525051738 | 7477577214 | Mahikjl66@gmail.com | 26°57'41.1"N 75°39'08.3"E | 230000 | 230000 | 230000 | 200000 | 30000 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 30000 | 200000 | 30000 | 230000 | 0
23 | LOAN APPLY | REENA | 3KW | 1PH | CANARA | HATHOJ | HATHOJ | 211529018405 | 9829841176 | Kumaryogesh9895@gmail.com | 26°58'54.3"N 75°40'47.8"E | 195000 | 175000 | 175000 | 175000 | 0 | File login | Center (78K) | File into bank | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 175000 | 0 | 175000
24 | HOLD | SHYOPAL | 3+5KW | 1PH | INDIAN | HATHOJ | HATHOJ | 211529013319 | 8387809024 |  |  | 225000 | 210000 | 210000 | 200000 | 10000 | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet |  |  |  |  | 10000 | 200000 | 10000 | 210000
25 | BILL ME NAME CHANGE | KALU RAM JAT | 3KW | 1PH | RGB | MANCHVA | KALWAR |  |  |  | 26°59'49.8"N 75°37'21.2"E | 200000 | 180000 | 180000 | 180000 | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 180000 | 0 | 180000
[16 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 0 | 0 | 0
[16 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 0 | 0 | 0
[16 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet | [7 empty] | 0
[16 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet

## SATAYNARAYAN JI
NO | UPDATE | NAME | KW | PH | BANK | LOCATION | DISCOM | K.NO | MOBILE | GMAIL | GPS / LINK | QUATATION IN BANK | FINAL DEAL WITH CLIENT | DEAL WITH MSS | LOAN | CASH | FILE LOGIN | SUBSIDY | BANK FILE/CASH | WORK STATUS | DISCOM WORK | PAYMENT STATUS | 1ST INSTALLMENT | 2ND INATALLMENT | CASH TO MSS | PAYMENT WITH PARTNER | CASH DUE FROM CLIENT | BANK DUE | CASH DUE TO MSS | NET DUE TO MSS | TOTAL PAYMENT RECIVED | REMARK
1 | DOCUMENTS PENDING | SAWARMAL YADAV | [7 empty] | Vky5111993@gmail.com | 27°07'47.7"N 75°34'36.4"E | 225000 |  |  |  | 0 | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet | [6 empty] | 0 |  | 0
2 | BANK SHOW NHI HO RHA | SHRAWAN YADAV | 3 | 1PH |  | KHERI MILK | JOBNER | 211543006758 | 9636956119 | rampalyadav9737@gmail.com | 27°04'41.1"N 75°24'48.2"E |  |  |  |  | 0 | COMPLET | Both (78 + 17) | Loan apply | Project On Hold | Pending | Payment Not Received Yet |  |  |  |  | 0 | 0 | 0 | 0 | 0
3 | LOAN APPLY | SOHNI DEVI | 3KW | 1PH | SBI | LALPURA | KALWAR | 211525007064 | 8005880815 | SOHANI231@GMAIL.COM | 26°58'38.0"N 75°31'27.2"E | 225000 | 200000 | 170000 | 200000 | 0 | File login | Both (78 + 17) | File into bank | Project On Hold | Pending | Payment Not Received Yet |  |  |  |  | 0 | 200000 | -30000 | 170000 | 0
1 | completed | PRAHLAD SAHAY YADAV | 3KW | 1PH | SBI | KHERI MILK | JOBNER | 211543033252 | 9799535224 | Psyadav5224@gmail.com | 27°04'12.4"N 75°25'13.6"E | 200000 | 180000 | 165000 | 180000 | 0 | COMPLET | Center (78K) | Loan approved | I&C Completed | Subsidy granted | 2ns Installment Received | 126000 | 54000 |  |  | 0 | 0 | -15000 | -15000 | 180000 | 15k extra expense from MSS side on the site
2 | completed | CHHOTU RAM | 3KW | 1PH | SBI | KHEDIMILAK | JOBNER | 211543024429 | 9602580089 | Rahulkhedi1997@Gmail.com | 27°04'09.3"N 75°25'43.8"E | 200000 | 180000 | 170000 | 180000 | 0 | COMPLET | Center (78K) | Loan approved | I&C Completed | Subsidy granted | 2ns Installment Received | 126000 | 54000 |  |  | 0 | 0 | -10000 | -10000 | 180000
3 | SUBSIDY PENDING | mangi devi | 3kw | 1PH | SBI | KHAK BABA | JOBNER | 211543031692 | 9950010084 | MALIRAMAMALIRAMAYADAVA465@GAMIL.COM | 27°04'45.8"N 75°27'14.1"E | 211000 | 190000 | 170000 | 189000 | 1000 | COMPLET | Center (78K) | Loan approved | I&C Completed | Subsidy apply with site photo | Payment Due | 132300 | 56700 |  |  | 1000 | 0 | -19000 | -19000 | 189000
4 | SUBSIDY PENDING | JAGDISH NARAYAN YADAV | 5KW | 1PH | SBI | KHERI MILK | JOBNER | 211543029486 | 9001854634 | JAGDISHYADAVMILK@GMAIL.COM |  | 225000 | 255000 | 250000 | 200000 | 55000 | COMPLET | Both (78 + 17) | Loan approved | I&C Completed | Subsidy apply with site photo | Payment Due | 140000 | 60000 |  |  | 55000 | 0 | 50000 | 50000 | 200000 | 50k cash hume dega
5 | SUBSIDY PENDING | SAROJ KANWAR | 6KW | 1PH | SBI | BHAINSAWA RD | JOBNER | 211543002919 | 8003778333 | NATHAWATBHOPALSINGH@GMAIL.COM | 27°02'45.6"N 75°28'46.0"E | 225000 | 355000 | 300000 | 200000 | 155000 | COMPLET | Center (78K) | Loan approved | I&C Completed | Subsidy apply with site photo | Payment Due | 140000 | 60000 |  |  | 155000 | 0 | 100000 | 100000 | 200000 | 100k cash dega
6 | METER, SUBSIDY PENDING | girdhari lal kumawat | 3kw | 1PH | RGM | MINDA | MAROTH | 110561009732 | 8741802877 | girdharilalk45@gmail.com | 27°07'02.6"N 75°19'01.0"E | 200000 | 180000 | 170000 | 180000 | 0 | COMPLET | Both (78 + 17) | Loan approved | I&C Completed | Meter & File submit DISCOM | 1st Installment Received | 126000 |  |  |  | 0 | 54000 | -10000 | 44000 | 126000
7 | METER, SUBSIDY PENDING | RAJ KUMAR YADAV | 3KW | 1PH | UCO | MANDA | RENWAL | 211544002801 | 8619004473 | RAJUBRAJUB23114@GMAIL.COM | 27°02'29.0"N 75°19'00.0"E | 211000 | 190000 | 170000 | 189000 | 1000 | COMPLET | Center (78K) | Loan approved | I&C Completed | Subsidy apply with site photo | Payment Due | 147000 | 64000 |  |  | 1000 | -22000 | -19000 | -41000 | 211000
8 | METER, SUBSIDY PENDING | JAGDISH PRASAD SHARMA | 5KW | 3PH | SBI | KARDHANI | JHOTWARA | 210474038323 | 9928051888 | atulmaism5@gmail.com | https://maps.app.goo.gl/6FbxTbDN5M5n4rGb8?g_st=ipc | 225000 | 260000 | 265000 | 200000 | 60000 | COMPLET | Both (78 + 17) | Loan approved | I&C Completed | Net Metering | 1st Installment Received | 140000 |  |  |  | 60000 | 60000 | 65000 | 125000 | 140000
9 | METER, SUBSIDY PENDING | MALI RAM YADAV | 3KW | 1PH | SBI | KHERI MILK | JOBNER | 211543016284 | 9928914848 | PCYADAV4446@GMAIL.COM | 27°03'45.0"N 75°25'56.5"E | 211000 | 190000 | 170000 | 189000 | 1000 | COMPLET | Center (78K) | Loan approved | I&C Completed | Meter & File submit DISCOM | 1st Installment Received | 132300 |  |  |  | 1000 | 56700 | -19000 | 37700 | 132300
10 | METER, SUBSIDY PENDING | BRIJESH KUMAR JANGID | 3KW | 1PH | SBI | KHERI MILK | JOBNER | 211543004068 | 9680139875 | MANISHJANGID 4145@GMAIL.COM | 27°04'09.1"N 75°25'42.7"E | 205000 | 185000 | 170000 | 185000 | 0 | COMPLET | Both (78 + 17) | Loan approved | I&C Completed | Meter & File submit DISCOM | 1st Installment Received | 128800 |  |  |  | 0 | 56200 | -15000 | 41200 | 128800
11 | METER, SUBSIDY PENDING | JAGMALA | 3KW | 1PH | BOI | MALIKPURA | RENWAL | 211544029437 | 9636953406 | ypappu9636@gmail.com | https://maps.google.com/?q=27.192663,75.400536 | 211000 | 190000 | 170000 | 189000 | 1000 | COMPLET | Center (78K) | Loan approved | I&C Completed | Meter & File submit DISCOM | 1st Installment Received | 94500 |  |  |  | 1000 | 94500 | -19000 | 75500 | 94500
12 | LOAN APPLY | CHITRA MAL | 3KW | 1PH | SBI | KHERI MILK | JOBNER | 211543004116 | 9982314035 | CMYADAV4035@GMAIL.COM |  | 211000 | 190000 | 170000 | 186000 | 4000 | File login | Both (78 + 17) | File into bank | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 4000 | 186000 | -16000 | 170000 | 0
13 | LOAN APPLY | KANARAM YADAV | 3KW | 1PH | PNB | KARANSAR | JOBNER | 211543010330 | 7297821259 | pawanshap5611@gmail.com | 27°05'46.8"N 75°26'15.3"E | 211000 | 190000 | 170000 | 189000 | 1000 | File login | Both (78 + 17) | File into bank | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 1000 | 189000 | -19000 | 170000 | 0
14 | LOAN APPLY | GOPAL LAL YADAV | 5KW | 1PH | SBI | KALADERA | KALADERA | 210516014667 | 9784846022 | SURESHYADAV15081992@GMAIL.COM | 27°07'47.7"N 75°34'36.4"E | 225000 | 255000 | 250000 | 200000 | 55000 | File login | Center (78K) | File into bank | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 55000 | 200000 | 50000 | 250000 | 0
15 | DOCUMENTS PENDING | LALCHAND VERMA | 6KW | [5 empty] | 7375098842 | lalchandverma211@gmail.com | 26°53'55.8"N 75°41'54.2"E |  |  |  |  | 0 | File login | Center (78K) | CASH FILE | Structure Work | Pending | Payment Not Received Yet |  |  |  |  | 0 | 0 | 0 | 0 | 0
16 | LOAN APPLY | KAJOD MAL YADAV | 3KW | 1PH | SBI | CHIRNOTIYA | JOBNER | 211543032330 | 7891492888 | KAJODMALYADAV100@GMAIL.COM | 26°59'53.2"N 75°25'12.4"E | 217000 | 195000 | 170000 | 195000 | 0 | File login | Center (78K) | File into bank | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 195000 | -25000 | 170000 | 0
17 | WORK START KRNA H | RISHABH PARWAL | 5KW | 1PH | SBI | GOVINDPURA | HATHOJ | 211529031375 | 7062933004 | rishabhparwal99@gmail.com | 26°57'44.8"N 75°42'09.0"E | 225000 | 270000 | 250000 | 200000 | 70000 | File login | Center (78K) | Loan approved | Structure Work | Meter & File submit DISCOM | 1st Installment Received | 140000 |  | 34000 |  | 36000 | 60000 | 16000 | 76000 | 174000
18 | FILE LOGIN | ATUL SHARMA | 3KW | 1PH |  | MANCHAVA | kalwar | 211525051970 | 9252880789 | atulelectrotech@gmail.com |  | 217000 | 195000 | 170000 | 195000 | 0 | File login | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 195000 | -25000 | 170000 | 0
19 | LOGIN | BALU RAM YADAV | 5KW |  |  | GOVINDPURA | JHOTWARA | 210474080523 | 9799179097 | NCY9799@GMAIL.COM | 26°57'06.3"N 75°41'50.9"E |  |  | 250000 |  | 0 | File login | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 0 | 250000 | 250000 | 0
20 | WORK START KRNA H | NARENDRA KUMAR | 5KW | 1PH | CANRA | NIWARU | HATHOJ | 211529025044 | 7340067237 | manisharajwaniya9@gmail.com | 26°57'45.9"N 75°42'27.5"E | 225000 | 278000 | 250000 | 200000 | 78000 | File login | Center (78K) | Loan approved | Work Not Started Yet | Meter & File submit DISCOM | 1st Installment Received | 116000 |  |  |  | 78000 | 84000 | 50000 | 134000 | 116000

## Rohit (RJ GREEN)
NO | UPDATE | NAME | KW | PH | BANK | LOCATION | DISCOM | K.NO | MOBILE | GMAIL | GPS / LINK | QUATATION IN BANK | FINAL DEAL WITH CLIENT | DEAL WITH MSS | LOAN | CASH | FILE LOGIN | SUBSIDY | BANK FILE/CASH | WORK STATUS | DISCOM WORK | PAYMENT STATUS | 1ST INSTALLMENT | 2ND INATALLMENT | CASH TO MSS | PAYMENT WITH PARTNER | CASH DUE FROM CLIENT | BANK DUE | CASH DUE TO MSS | NET DUE TO MSS | TOTAL PAYMENT RECIVED | REMARK
1 | LOAN APPLY | RANI DEVI | 3KW | 1PH |  | JAISINGHPURA | AMBER | 210454044569 | 9079254660 | SNJITINKER@GMAIL.COM | 26°57'20.5"N 75°52'49.6"E | 200000 | 180000 | 177000 | 180000 | 0 | File login | Both (78 + 17) | Loan Rejected | Project On Hold | Pending | Payment Not Received Yet
1 | COMPLETED | URMILA NAREDI | 3KW | 1PH | SBI | CHORA RASTA | KANOTA | 210594027238 | 9529076165 | RAKESHJEWELLRY@GMAIL.COM | 26°53'23.8"N 75°55'12.8"E | 200000 | 180000 | 175000 | 180000 | 0 | COMPLET | Both (78 + 17) | Loan approved | I&C Completed | Subsidy granted | 2ns Installment Received | 125000 | 55000 |  |  | 0 | 0 | -5000 | -5000 | 180000
2 | COMPLETED | INDRA DEVI VIJAY | 5KW | 1PH |  | DHAWAS | BHANKHROTA | 210413009576 | 9829776972 | mithleshkumar.sgi@gmail.com |  | 250000 | 250000 | 245000 | 0 | 250000 | COMPLET | Both (78 + 17) | CASH FILE | I&C Completed | Subsidy granted | Cash To Mahi | 0 | 0 | 230000 | 20000 | 0 | 0 | 15000 | 15000 | 250000
3 | COMPLETED 17K PENDING | RUKMANI DEVI AGRAWAL | 5KW | 3PH |  | SANGANER | SANGANER | 211463034631 | 9468741041 | jainlucky31@gmail.com | 26°48'40.2"N 75°47'47.9"E | 285000 | 280000 | 255000 | 0 | 280000 | COMPLET | Both (78 + 17) | CASH FILE | I&C Completed | Subsidy granted | Payment Due | 0 | 0 | 243000 | 20000 | 17000 | 0 | 12000 | 12000 | 263000
4 | COMPLETED | KANTA DEVI | 4KW | 1PH | SBI | KUNDA | AMBER | 210454028738 | 9636938730 | alokbhat6008@gmail.com | 26°59'37.1"N 75°52'52.4"E | 225000 | 200000 | 200000 | 190000 | 10000 | COMPLET | Both (78 + 17) | Loan approved | I&C Completed | Subsidy granted | Payment Due | 120000 | 70000 |  |  | 10000 | 0 | 10000 | 10000 | 190000
5 | COMPLETED | ARVIND RAJVANSHI | 5KW | 3PH | SBI | DHAWAS | BHANKHROTA | 210413076509 | 8239019052 | arvindrajwanshi8239019052@gmail.com | 26°53'35.3"N 75°43'16.9"E | 225000 | 280000 | 255000 | 200000 | 80000 | COMPLET | Center (78K) | Loan approved | I&C Completed | Subsidy granted | Payment Due | 140000 | 60000 | 20000 |  | 60000 | 0 | 35000 | 35000 | 220000
6 | COMPLETED | roopnarayn kumawat | 3KW | 1ph | SBI | DHAWAS | BHANKHROTA | 210413056350 | 9549557237 | roopkumawat90@gmail.com | 26°53'37.1"N 75°43'01.1"E | 225000 | 200000 | 158894 | 200000 | 0 | COMPLET | Both (78 + 17) | Loan approved | I&C Completed | Subsidy granted | 2ns Installment Received | 140000 | 54000 | 18894 |  | -18894 | 6000 | -60000 | -54000 | 212894
7 | METER,SUBSIDY PENDING | URMILA DEVI KUMAWAT | 3kw | 1ph | SBI | DHAWAS | BHANKHROTA | 210413030461 | 9829301102 | g.k7843@gmail.com | 26°53'38.6"N 75°42'45.8"E | 200000 | 180000 |  | 180000 | 0 | COMPLET | Both (78 + 17) | Loan approved |  | Meter & File submit DISCOM | 1st Installment Received | 126000 |  |  |  | 0 | 54000 | -180000 | -126000 | 126000
8 | HOLD | MUNNI DEVI | 5KW | 3PH |  |  |  | 211534053695 | [7 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet |  |  |  |  | 0 | 0 | 0 | 0 | 0
9 | DOCUMENTS PENDING | POOJA KUMAWAT | 3KW | 1PH | PNB | BAGRU | BAGRU | 211534058665 | 8947876609 |  | 26°50'06.8"N 75°32'46.4"E | 200000 | 180000 |  | 180000 | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 180000 | -180000 | 0 | 0
[16 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 0 | 0 | 0 | 0
[16 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 0 | 0 | 0 | 0
[16 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 0 | 0 | 0 | 0
[16 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 0 | 0 | 0 | 0
[16 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 0 | 0 | 0 | 0
[16 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 0 | 0 | 0 | 0

## CALL TEAM SITE
NO | update | NAME | KW | PH | BANK | LOCATION | DISCOM | K.NO | MOBILE | GMAIL | GPS / LINK | QUATATION IN BANK | FINAL DEAL with client | LOAN | Cash | File login | SUBSIDY | BANK FILE/CASH | WORK STATUS | DISCOM WORK | PAYMENT STATUS | 1ST INSTALLMENT | 2ND INATALLMENT | CASH TO MSS | Bank due | CASH DUE FROM CLIENT | NET DUE TO MSS | TOTAL Payment recieved | REMARK
1 | HOLD | RAJESH KUMAR | 5KW |  |  | SIRSI | BINAYAKA | 210416034452 | 9815614316 | RAJESH.DEEPAK85@GMAIL.COM | [5 empty] | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
2 | PROPERTY DISPUTE CHAL RHA H HOLD | RAMSWROOP VERMA | 3KW | 1PH |  | JOBNER | JOBNER | 211543031438 | 9001553194 | RAMSAWROOP9001@GMAIL.COM | 26°57'08.3"N 75°41'50.2"E |  | 190000 |  | 190000 | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet |  |  |  | 0 | 190000 | 190000 | 0
8 | VENDOR CHANGE HOGA | HAJARI SINGH | 5KW | 1PH | SBI |  | MURLIPURA | 210473018061 | 8441060660 | vss1443@gmail.com | 26°59'12.5"N 75°45'26.9"E | 260000 | 260000 |  | 260000 | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet |  |  |  | 0 | 260000 | 260000 | 0
5 | BILL ME NAME TRANSFER | GOVIND GUPTA | 3KW | 1PH |  |  | PURANA GHAT | 211444008828 | 9414443150 |  | 26°53'07.8"N 75°53'56.8"E | 200000 | 180000 | 180000 | 0 | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet |  |  |  | 180000 | 0 | 180000 | 0
4 | BILL ME NAME UPDATE HOGA | SITARAM MEENA | 5KW | 1PH | BOB | KOKAWAS | SHIKARPURA | 211467008062 | 9660209863 | SM6705242@GMAIL.COM | 26°46'06.6"N 75°46'30.9"E | 225000 | 280000 |  | 280000 | File login | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet |  |  |  | 0 | 280000 | 280000 | 0
6 | private bank se hogi | VINOD YADAV | 3KW | 1PH |  |  | jalso | 211528020871 | 9602939503 | kaluramyadav907@gmail.com | 27°07'46.1"N 75°40'42.4"E |  | 185000 |  | 185000 | File login | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet |  |  |  | 0 | 185000 | 185000 | 0
7 | DOCUMENTS PENDING | MAHENDRA(NON DCR) | 5KW | 1PH |  |  | BHANKROTA | 210413057989 | 9385393952 |  |  |  | 230000 |  | 230000 | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet |  |  |  | 0 | 230000 | 230000 | 0
8 | BILL ME CORRECTION HOGA | OMPRAKESH JANGID | 3KW | 1PH |  |  | BHANKROTA | 210413022219 | 9414360051 | OMPRAKASHJANGID262@GMAIL.COM |  |  |  |  | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 0 | 0 | 0 | 0
6 | DOCUMENTS PENDING | JITENDRA JAJORIA | 3KW | 1PH |  |  | JOBNER | 211543017739 | 9667092633 | jkjajoria886@gmail.com | XGM3+56J, Bassi Naaga, Rajasthan 303124 | 200000 | 180000 | 180000 | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 180000 | 0 | 180000 | 0
1 | private bank se hogi | KHEMARAM BAJDOLIYA | 5KW | 1PH |  | JOBNER | JOBNER | 211543026446 | 9784416781 | KHAMRAJJAAT789@GMAIL.COM |  |  |  |  | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 0 | 0 | 0 | 0
2 | LOAN APPLY | INDRAJ KUMAR MEENA | 3KW | 1PH | BOB | JOBNER | JOBNER | 211543031711 | 9887131382 | aalakabas6277@gmail.com | https://maps.app.goo.gl/tLo1CgfxC3gx5N158?g_st=aw | 211000 | 190000 | 189000 | 1000 | File login | Center (78K) | File into bank | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 189000 | 1000 | 190000 | 0
3 | LOAN APPLY | ASHA | 5KW | 1PH | BOB | NIWARU | HATHOJ | 211529020427 | 9024153918 | ashasekhawat@626gmail.com | 26°58'46.4"N 75°43'06.5"E | 225000 | 285000 | 200000 | 85000 | File login | Center (78K) | File into bank | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 200000 | 85000 | 285000 | 0
4 | WORK START KRNA | MEENA MEENA | 5KW | 1PH | SBI | SANGNAER | SANGANER | 211584063188 | 9711666861 | smsureshmeena06@gmail.com | https://maps.app.goo.gl/NHah8eNnzHvqbRbp8?g_st=aw | 265000 | 265000 | 200000 | 65000 | File login | Center (78K) | Loan approved | Material & Team Reached | Meter & File submit DISCOM | 1st Installment Received | 140000 |  |  | 60000 | 65000 | 125000 | 140000
5 | ADHAR ME DOB CHANGE HOGI | SHANKR LAL KUMAWAT | 3KW | 1PH |  |  | JOBNER | 211543016040 | 9602142643 | sitaramkumawat9709@gmail.com |  |  |  |  | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 0 | 0 | 0 | 0
6 | FILE LOGIN | DEEPAK SHARMA | 5KW | 3PH |  | GOPALPURA | DURGAPURA | 211424033011 | 8949396288 | sharma.deepak267@gmail.com | 26°52'14.3"N 75°46'17.8"E | 280000 | 280000 | 0 | 280000 | File login | Center (78K) | CASH FILE | Material & Team Reached | Meter & File submit DISCOM | Payment Due |  |  | 25000 | 0 | 255000 | 255000 | 25000
7 | FILE LOGIN | ashok sharma | 3kw | 3PH |  | GOPALPURA | DURGAPURA | 211424001098 | 9784063533 | sharma.ashokmes@gmail.com | 26°52'14.3"N 75°46'17.8"E | 200000 | 200000 | 0 | 200000 | File login | Center (78K) | CASH FILE | Material & Team Reached | Meter & File submit DISCOM | Payment Due |  |  | 25000 | 0 | 175000 | 175000 | 25000
8 | DOCUMENTS PENDING | MAINA DEVI | 3KW | 1PH | SBI |  | KALWAR | 211525048383 |  |  | 26°57'12.4"N 75°43'10.5"E |  |  |  | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 0 | 0 | 0 | 0
9 | LOAN APPLY | MUKESH KUMAR PERWA | 5KW | 1PH | BOB |  | RAMGANJ | 210452054648 | 8239217331 | Mukeshparewa50@gmail.com | 26°55'27.6"N 75°50'35.7"E | 260000 | 260000 | 200000 | 60000 | File login | Center (78K) | File into bank | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 200000 | 60000 | 260000 | 0
[15 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 0 | 0 | 0 | 0
[15 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 0 | 0 | 0 | 0
[15 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  | 0 | 0 | 0 | 0

## POORAN JI
S.R | UPDATE | NAME | KW | PH | LOCATION | DISCOM | K.NO | MOBILE | GMAIL | GPS / LINK | QUATATION IN BANK | FINAL DEAL WITH CLIENT | DEAL WITH MSS | LOAN | CASH | FILE LOGIN | SUBSIDY | BANK FILE/CASH | WORK STATUS | DISCOM WORK | PAYMENT STATUS | 1ST INSTALLMENT | 2ND INATALLMENT | CASH TO MSS | PAYMENT WITH PARTNER | CASH DUE FROM CLIENT | BANK DUE | CASH DUE TO MSS | NET DUE TO MSS | TOTAL PAYMENT RECIVED | REMARK
1 | DOCUMENTS PENDING | SITA RAM KUMAWAT |  |  |  | GOVINDGARH | 210513022788 | 9001959864 | KINDESTMAHENDRA927@GMAIL.COM | [5 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet
2 | LOAN APLLY | GULAB CHAND KUMAWAT | 5KW | 3KW | CHOMU | CHOMU | 210511032510 | 9785262235 | Pk191292@gmail.com | 27°09'41.4"N 75°42'42.9"E | 280000 | 280000 |  | 200000 | -200000 | File login | Center (78K) | File into bank | Work Not Started Yet | Pending | Payment Not Received Yet
3 | LOAN APLLY | GITA DEVI | 3KW | 1PH | RENWAL | RENWAL | 211544023998 | 8058185887 | tarachandkmwt635@gmail.com | 27°09'14.8"N 75°21'11.9"E | 225000 |  |  | 200000 | -200000 | File login | Center (78K) | File into bank | Work Not Started Yet | Pending | Payment Not Received Yet
4 | [14 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet
[15 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet
[15 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet
[15 empty] | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet

## Ajay (everest)
NO | UPDATE | NAME | KW | PH | LOCATION | DISCOM | K.NO | MOBILE | GMAIL | GPS / LINK | QUATATION IN BANK | FINAL DEAL WITH CLIENT | DEAL WITH MSS | LOAN | CASH | FILE LOGIN | SUBSIDY | BANK FILE/CASH | WORK STATUS | DISCOM WORK | PAYMENT STATUS | 1ST INSTALLMENT | 2ND INATALLMENT | CASH TO MSS | PAYMENT WITH PARTNER | CASH DUE FROM CLIENT | BANK DUE | CASH DUE TO MSS | NET DUE TO MSS | TOTAL Payment recieved | Remark
1 | COMPLETED | KAILASH CHAND KUMAWAT | 3KW | 1PH | PHULERA | SAMBHAR | 211541027257 | 9636562714 | KAILASHKUMAWAT1001@GMAIL.COM |  | 200000 | 180000 | 28117 | 180000 | 0 | File login | Both (78 + 17) | Loan approved | I&C Completed | Subsidy granted | 2ns Installment Received | 110000 | 70000 | 0 |  | 0 | 0 | -151883 | -151883 | 180000 | Done
2 | meter,subsiday pending | PUSHPA | 3KW | 1PH | JHOTWARA | JHOTWAR | 210474058651 | 8619075272 | Shubhamsinghc570@gmail.com | 26.9422621, 75.7177459 | 200000 | 190000 | 21228 | 0 | 190000 | File login | Both (78 + 17) | CASH FILE | I&C Completed | Meter & File submit DISCOM | Payment Not Received Yet | 0 | 0 | 0 |  | 190000 | 0 | 21228 | 21228 | 0 | Done
3 | FILE LOGIN | SURENDRA KUMAR (mayank) | 8kw | 3PH | Gandhi PATH | VAISHALI NAGAR | 210413075570 | 9314064698 | Surendersanghi 38 @ gmail.com |  | 370000 | 370000 | 325500 | 0 | 370000 | File login | Center (78K) | Loan apply | I&C Completed | Pending | Payment Due | 0 | 0 | 296500 | 73500 | 0 | 0 | 29000 | 29000 | 370000 | Done
4 | FILE LOGIN | KAILASHI DEVI | 3KW | 1PH | JHOTWARA | SHALIMAR_CHORHA | 210475019747 | 9928252415 | jpsharmaji724@gmail.com |  | 180000 | 180000 | 27626 |  | 180000 | File login | Both (78 + 17) | CASH FILE |  | Meter & File submit DISCOM | Payment Not Received Yet | 0 | 0 | 0 |  | 180000 | 0 | 27626 | 27626 | 0 | Done
5 | FILE LOGIN | DINESH KUMAWAT | 3KW | 1PH | PHULERA | SAMBHAR | 211541041408 | 7728826118 | dk6100239@gmail.com | 26°52'11.5"N 75°15'09.8"E | 210000 | 200000 | 2000 | 200000 | 0 | File login | Center (78K) | Loan approved |  | Pending | 1st Installment Received | 110000 | 0 | 0 |  | 0 | 90000 | -198000 | -108000 | 110000 | Done
6 | FILE LOGIN | MITHLESH KANWAR | 5KW |  | KARINI PATAK | JHOTWARA | 210474028377 | 9828187773 | vishalsinghshekhawat17@gmail.com |  | 290000 | 290000 | 2000 | 0 | 290000 | File login | Center (78K) | CASH FILE |  | Meter & File submit DISCOM | Payment Not Received Yet | 0 | 0 | 0 |  | 290000 | 0 | 2000 | 2000 | 0
7 | FILE LOGIN | RAMRATAN VERMA | 3KW | 1PH | PHULERA | SAMBHAR | 211541032593 | 9784002424 | Ramratanv24@gmail.com | 26°52'00.3"N 75°14'34.3"E | 225000 | 200000 | 2000 | 200000 | 0 | File login | Both (78 + 17) | File into bank |  | Meter & File submit DISCOM | 1st Installment Received | 100000 | 0 | 0 |  | 0 | 100000 | -198000 | -98000 | 100000
8 | 1ST PAYMENT DONE | MANBHAR DEVI | 5KW | 1PH | GOVINPURA | HATHOJ | 211529010283 | 8690250029 |  | 26°57'07.9"N 75°41'25.0"E | 220000 | 200000 | 2000 | 199000 | 1000 | File login | Both (78 + 17) | Loan approved |  | Meter & File submit DISCOM | 1st Installment Received | 139000 | 0 | 0 |  | 1000 | 60000 | -197000 | -137000 | 139000 | Done
9 | LOAN APPLY | SUMITRA | 3KW | 1PH | NIWARU | HATHOJ | 211529012243 | 7691830457 | rkishan2674@gmail.com |  | 225000 | 200000 | 2000 | 200000 | 0 | File login | Center (78K) | File into bank |  | Pending | 1st Installment Received | 140000 | 0 | 0 |  | 0 | 60000 | -198000 | -138000 | 140000
10 | LOGIN | SANJU DEVI | 8KW | 3PH | NIWARU | HATHOJ | 211529013111 | 8078602223 | Dhillonvijay662@gmail.com | 26°58'21.5"N 75°42'21.5"E | 250000 |  | 2000 |  | 0 | File login | Center (78K) | CASH FILE |  | Pending | Payment Not Received Yet | 0 | 0 | 0 |  | 0 | 0 | 2000 | 2000 | 0
11 | LOAN APPLY | HEENA BANO | 3KW | 1PH | PHULERA | SAMBHAR | 211541037380 | 8949711161 | HKHAN39019@GMAIL.COM |  | 225000 | 200000 | 2000 | 200000 | 0 | File login | Center (78K) | File into bank |  | Pending | 1st Installment Received | 110000 | 0 | 0 |  | 0 | 90000 | -198000 | -108000 | 110000
12 | LOGIN | HASEENA BANO | 6KW | 3PH | JHOTWARA | SHALIMAR_CHORHA | 210475040846 | 9667711380 | Aveshnizamkhani@gmail.com | https://maps.app.goo.gl/X2zbd1dBz4cJG7EW8?g_st=awb | 230000 | 340000 | 227193 | 0 | 340000 | File login | Both (78 + 17) | CASH FILE | I&C Completed | Net Metering | Payment Not Received Yet | 0 | 0 | 140000 | 110000 | 90000 | 0 | 87193 | 87193 | 250000 |  | bill expense update honge
13 | FILE LOGIN | LAXMI NARAIN KUMAWAT | 5KW | 1PH | PHULERA | SAMBHAR | 211541027285 | 7792961082 | babulal2797@gmail.com | 26°52'22.9"N 75°15'27.2"E | 225000 |  |  |  | 0 | File login | Both (78 + 17) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 0 | 0 | 0 | 0
14 | LOAN REJECT NHI HUA | BIMLA DEVI | 5KW |  | KANAKPURA | JHOTWARA | 210474057868 | 8769243716 | sumersingh246x@gmail.com | 26°56'00.7"N 75°43'05.7"E | 225000 | 290000 |  | 200000 | 90000 | File login | Center (78K) | File into bank | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 90000 | 200000 | -200000 | 0 | 0
15 | FILE LOGIN | MADAN LAL | 3KW | 1PH | PHULERA | SAMBHAR | 211541034723 | 9950288449 | MADANLALPHULERA@GMAIL.COM | 26°52'15.2"N 75°15'07.9"E | 225000 | 200000 | 2000 | 200000 | 0 | File login | Both (78 + 17) | File into bank |  | Meter & File submit DISCOM | Payment Not Received Yet |  |  |  |  | 0 | 200000 | -198000 | 2000 | 0
16 | BANK SHOW NHI HO RHA | KAMLESH CHOUHAN | 5KW | 3PH | BAD KE BALAJI | BAGRU | 211534018670 | 9982012155 | ranichouhan1577@gmail.com | 26°49'31.3"N 75°37'40.5"E | 330000 |  |  |  | 0 | File login | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 0 | 0 | 0 | 0
17 | LOAN APPLY | POONAM DEVI | 3KW | 1PH | NIWARU | HATHOJ | 211529021831 | 9660032534 | ryadav03oct1980@gmail.com |  | 225000 |  | 2000 | 200000 | -200000 | File login | Center (78K) | File into bank |  | Meter & File submit DISCOM | 1st Installment Received | 140000 |  |  |  | -200000 | 60000 | -198000 | -138000 | 140000
18 | LOAN APPLY | JITENDRA SHARMA | 3KW | 1PH | PHULERA | SAMBHAR | 211541024194 | 9660724348 | JEETENDRASHARMA9660724348@GMAIL.COM | 26°52'22.3"N 75°15'08.7"E | 225000 |  | 2000 | 200000 | -200000 | File login | Center (78K) | File into bank |  | Pending | 1st Installment Received | 140000 |  |  |  | -200000 | 60000 | -198000 | -138000 | 140000
19 | LOAN APPLY | PATASI DEVI | 3KW | 1PH | HATHOJ | HATHOJ | 211529027957 | 72401 39113 | MAHENDRAKUMARA1212131@GMAIL.COM |  | 220000 |  |  | 198000 | -198000 | File login | Center (78K) | File into bank | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | -198000 | 198000 | -198000 | 0 | 0
20 | LOAN APPLY | BHAWARI DEVI | 3KW | 1PH | HATHOJ | HATHOJ | 211529038865 | 7062232032 | KUMAWATMONU813@GMAIL.COM | https://goo.gl/maps/vNkPP3VEgzyj8kmZ9?g_st=ac | 225000 |  | 2000 | 200000 | -200000 | File login | Center (78K) | File into bank |  | Pending | 1st Installment Received | 140000 |  |  |  | -200000 | 60000 | -198000 | -138000 | 140000
21 | LOAN APPLY | ASHOK KUMAR SHARMA | 3KW | 1PH | BAGRU | BAGRU | 211534052241 | 8952871961 | PARUL4377@GMAIL.COM | 26°49'18.9"N 75°32'38.1"E | 225000 |  |  | 200000 | -200000 | File login | Center (78K) | File into bank | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | -200000 | 200000 | -200000 | 0 | 0
22 |  | CHOGA LAL CHOUDHARY | 3KW | 1PH | PHULERA | SAMBHAR | 211541041283 | 7006858409 | C94253872@GMAIL.COM |  | 225000 | 200000 | 2000 | 190000 | 10000 | File login | Center (78K) | Loan apply |  | Pending | 1st Installment Received | 133000 |  |  |  | 10000 | 57000 | -188000 | -131000 | 133000
23 |  | MADAN LAL SHARMA | 3KW | 1PH | NIWARU | JHOTHWARA | 210474056335 | 9602958544 | RAKESHSHARMA242002@GMAIL.COM |  | 150000 | 150000 |  | 0 | 150000 | Doc Recieved | Center (78K) | CASH FILE | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 150000 | 0 | 0 | 0 | 0
24 |  | MUNESH DEVI | 3KW | 1PH | NIWARU | HATHOJ | 211529012293 | 7618141701 | hariramrawat074@mail.com |  | 225000 | 200000 | 2000 | 200000 | 0 | Doc Recieved | Center (78K) | Loan apply |  | Pending | 1st Installment Received | 140000 |  |  |  | 0 | 60000 | -198000 | -138000 | 140000
25 |  | GOPAL KRISHAN SHARMA | 5KW |  | BAGRU | BAGRU | 211534063633 | 9636395002 | gs6725039@gmail.com |  | 225000 |  |  |  | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 0 | 0 | 0 | 0
26 |  | HARISH KUMAR PARWANI | 3KW | 1PH | NIWARU | HATHOJ | 211529011054 | 9636179040 | geetah101081@gmail.com |  | 225000 | 200000 |  | 200000 | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 200000 | -200000 | 0 | 0
27 |  | SAJNI DEVI | 5KW | 1PH | PHULERA | SAMBHAR | 211541037379 | 7851066584 | dilrajbukan2@gmail.com |  | 225000 | 200000 |  | 200000 | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 200000 | -200000 | 0 | 0
28 |  | MOHAN LAL | 5KW | 1PH | JOBNER | JOBNER | 211543025300 | 9982510591 | BUSINESSJAATAJAY1998@GMAIL.COM |  | 225000 | 200000 |  | 200000 | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 200000 | -200000 | 0 | 0
29 |  | SANTOSH KANWAR | 3KW | 1PH | MANCHWA | KALWAR | 211525008286 | 9983311557 | RAJHUVEERSINGH474@GMAIL.COM |  | 225000 | 200000 |  | 200000 | 0 | Doc Recieved | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 200000 | -200000 | 0 | 0

## RAVI JI SITES
3 | UPDATE | NAME | KW | PH | LOCATION | DISCOM | K.NO | MOBILE | GMAIL | GPS / LINK | QUATATION IN BANK | FINAL DEAL WITH CLIENT | DEAL WITH MSS | LOAN | CASH | FILE LOGIN | SUBSIDY | BANK FILE/CASH | WORK STATUS | DISCOM WORK | PAYMENT STATUS | 1ST INSTALLMENT | 2ND INATALLMENT | CASH TO MSS | PAYMENT WITH PARTNER | CASH DUE FROM CLIENT | BANK DUE | CASH DUE TO MSS | NET DUE TO MSS | TOTAL PAYMENT RECIVED | REMARK
1 | LOGIN | RAMESH CHAND SHARMA | 5KW | 1PH | MEENAWALA | BINAYAKA | 210416018241 | 9950114385 | rameshpradhan4385@gmail.com |  | 270000 | 270000 |  | 0 |  | File login | Center (78K) | CASH FILE | I&C Completed | Subsidy apply with site photo | Payment Due |  |  |  |  | 0 | 0 | 0 | 0 | 0
2 | LOAN APPLY | RAKESH KUMAR SHARMA | 6KW | 1PH |  | JAGATAPURA | 211483068188 | 9928896930 | rakesh.baknad@gmail.com | 26°49'46.2"N 75°49'31.2"E | 225000 | 290000 |  | 200000 | 90000 | File login | Center (78K) | File into bank | I&C Completed | Subsidy apply with site photo | 1st Installment Received | 140000 |  |  |  | 90000 | 60000 | -200000 | -140000 | 140000
3 | LOGIN | ARUN KUMAR JOSHI | 6KW | 1PH |  |  | 211483067929 | 9461046995 | ARUNKUMARJOSHIARUN@GMAIL.COM | [6 empty] | File login | Center (78K) | CASH FILE | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 0 | 0 | 0 | 0
4 | LOGIN | phukraj | 6KW | 1PH |  |  |  | 9829766216 |  | 26°49'48.4"N 75°49'25.7"E | [5 empty] | File login | Center (78K) | CASH FILE | I&C Completed | Pending | Payment Not Received Yet
5 | LOGIN | kajodi lal | 6KW | 1PH |  |  |  | 9024680333 |  | 26°48'57.0"N 75°48'12.0"E | [5 empty] | File login | Center (78K) | CASH FILE | I&C Completed | Pending | Payment Not Received Yet
6 | LOGIN | SUNIL KUMAR | 3.7KW | 1PH | [11 empty] | File login | Center (78K) | CASH FILE | Work Not Started Yet | Pending | Payment Not Received Yet

## ravi inc
no. | UPDATE | name | kw | ph | location | number | WORK STATUS | Bill Total | Payment Received
1 | COMPLETED | phukraj | 6kw | 1ph | 26°49'48.4"N 75°49'25.7"E | 9829766216 | I&C Completed
2 | COMPLETED | kajodi lal | 6kw | 1ph | 26°48'57.0"N 75°48'12.0"E | 9024680333 | I&C Completed
3 | COMPLETED | SAURABH KANSAL | 6kw | 3PH |  |  | I&C Completed
4 | COMPLETED | SUNIL | 3.5KW | 1PH | Karolan Ka Barh, Jeerota, Jaipur, Rajasthan 302022 |  | I&C Completed
5 |  | KSHANTI DEVI | 6KW | 3PH | 26°49'48.4"N 75°49'25.7"E |  | Structure Work
6 |  | OMPARKASH | 3KW | 1PH | 26°49'28.1"N 75°33'48.5"E | 9772727474 | Work Not Started Yet
Work Not Started Yet
Work Not Started Yet
Work Not Started Yet
Work Not Started Yet

## dilkhush inc
no. | UPDATE | name | kw | ph | location | number | WORK STATUS | BILL TOATL | PAYMENT RECEIVED
1 | COMPLETED | ANURAG BUTOLIA | 3KW | 1PH | https://maps.app.goo.gl/HJmFhQmTsbCkvEwN8?g_st=aw | 9829025678 | I&C Completed
2 | COMPLETED | PRADHAN VAISHNAV | 5KW | 1PH | 26°57'40.3"N 75°43'05.4"E | 9782978040 | I&C Completed
3 | [6 empty] | Work Not Started Yet
4 | [6 empty] | Work Not Started Yet
Work Not Started Yet
Work Not Started Yet

## ROHIT JI PHULERA
NO | UPDATE | NAME | KW | PH | LOCATION | DISCOM | K.NO | MOBILE | GMAIL | GPS / LINK | QUATATION IN BANK | FINAL DEAL WITH CLIENT | DEAL WITH MSS | LOAN | CASH | FILE LOGIN | SUBSIDY | BANK FILE/CASH | WORK STATUS | DISCOM WORK | PAYMENT STATUS | 1ST INSTALLMENT | 2ND INATALLMENT | CASH TO MSS | PAYMENT WITH PARTNER | CASH DUE FROM CLIENT | BANK DUE | CASH DUE TO MSS | NET DUE TO MSS | TOTAL PAYMENT RECIVED | REMARK
1 | FILE LOGIN | SITA RAM KUMAWAT | 3KW |  | PHULERA | SAMBHAR | 211541040785 | 8094681907 | Seetaramkumawat1907@gmail.com | 26°52'27.2"N 75°17'51.5"E | 190000 | 170000 | 170000 | 171000 | -1000 | COMPLET | Center (78K) | Loan approved | I&C Completed | Pending | 2ns Installment Received | 119000 | 52000 |  |  | -1000 | 0 | -1000 | -1000 | 171000
| FILE LOGIN | NEERAJ GUPTA | 3KW | 1PH |  |  | 211443042169 | 9414300843 | Techie.shivam93@gmail.com | [9 empty] | Work Not Started Yet
Work Not Started Yet
Work Not Started Yet
Work Not Started Yet

## JITENDRA JI
NO | UPDATE | NAME | KW | PH | LOCATION | DISCOM | K.NO | MOBILE | GMAIL | GPS / LINK | QUATATION IN BANK | FINAL DEAL WITH CLIENT | DEAL WITH MSS | LOAN | CASH | FILE LOGIN | SUBSIDY | BANK FILE/CASH | WORK STATUS | DISCOM WORK | PAYMENT STATUS | 1ST INSTALLMENT | 2ND INATALLMENT | CASH TO MSS | PAYMENT WITH PARTNER | CASH DUE FROM CLIENT | BANK DUE | CASH DUE TO MSS | NET DUE TO MSS | TOTAL PAYMENT RECIVED | REMARK
1 | DOCUMENTS PENDING | ARUNA PALIWAL | 5KW | 1PH |  | BAGRU | 211534061705 | 8015926535 | paliwalmadanlal147@gmail.com | [5 empty] | 0 | File login | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 0 | 0 | 0 | 0
[16 empty] | File login | Center (78K) | Loan apply | Work Not Started Yet | Pending | Payment Not Received Yet
[16 empty] | File login | Center (78K) |  | Work Not Started Yet | Pending | Payment Not Received Yet
[16 empty] | File login | Center (78K) |  | Work Not Started Yet | Pending | Payment Not Received Yet
File login

## KAVITA MAM
NO | UPDATE | NAME | KW | PH | LOCATION | DISCOM | K.NO | MOBILE | GMAIL | GPS / LINK | QUATATION IN BANK | FINAL DEAL WITH CLIENT | DEAL WITH MSS | LOAN | CASH | FILE LOGIN | SUBSIDY | BANK FILE/CASH | WORK STATUS | DISCOM WORK | PAYMENT STATUS | 1ST INSTALLMENT | 2ND INATALLMENT | CASH TO MSS | PAYMENT WITH PARTNER | CASH DUE FROM CLIENT | BANK DUE | CASH DUE TO MSS | NET DUE TO MSS | TOTAL PAYMENT RECIVED | REMARK
1 | completed | PUNAM CHAND | 5KW | 3PH | BENAD | BADPEEPLI | 211522046354 | 9799033076 | poonamchand8682@gmail.com | 26°59'53.4"N 75°44'14.4"E | 257000 | 257000 | 242000 | 0 | 257000 | COMPLET | Center (78K) | CASH FILE | I&C Completed | Net Metering | Cash To Mahi | 0 | 0 | 180000 | 0 | 77000 | 0 | 62000 | 62000 | 180000 | 7k extra expense payment
2 | completed | PARAG MANGAL | 5KW | 1PH | sanganer | NIRMAN NAGAR | 211426010896 | 8890493989 | paragmangal.75@gmail.com | 26°53'08.8"N 75°45'11.8"E | 225000 | 270000 | 225000 | 200000 | 70000 | COMPLET | Center (78K) | Loan approved | I&C Completed | Subsidy apply with site photo | 2ns Installment Received | 140000 | 60000 | 70000 |  | 0 | 0 | -45000 | -45000 | 270000
3 | completed, | SANTOSH KUMAWAT | 6KW | 1PH | LALKOTHI | PATRAKAR | 211466025790 | 8385925902 | mohitkumawat2909@gmail.com | 26°51'56.8"N 75°45'04.0"E | 225000 | 285000 | 267000 | 200000 | 85000 | COMPLET | Both (78 + 17) | Loan approved | I&C Completed | Subsidy granted | 1st Installment Received | 140000 | 60000 | 75000 |  | 10000 | 0 | -8000 | -8000 | 275000
4 | completed | SANJAY KUMAR SHARMA | 5KW | 3PH | CHANDPOL | BAGRU | 211534052734 | 9079610549 | sanjaysharma01091975@gmail.com | 26°50'05.2"N 75°42'16.8"E | 225000 | 285000 | 235000 | 200000 | 85000 | COMPLET | Center (78K) | Loan approved | I&C Completed | Subsidy granted | 2ns Installment Received | 140000 | 60000 | 80000 |  | 5000 | 0 | -45000 | -45000 | 280000
5 | SUBSIDY 2 ND PAYMENT PENDING | MADAN MOHAN SHARMA | 6KW | 3PH | SANGANER | PATRAKAR_COLONY | 211466020013 | 9828736759 | MMSHARMA354@GMAIL.COM | 26°51'18.3"N 75°44'34.0"E | 225000 | 305000 | 280000 | 200000 | 105000 | COMPLET | Center (78K) | Loan approved | I&C Completed | Subsidy apply with site photo | 1st Installment Received | 140000 |  |  | 0 | 105000 | 60000 | 80000 | 140000 | 140000
6 | FILE LOGIN | ABHA | 5KW | 3PH | SANGANER | PATRAKAR_COLONY | 211466000548 | 9784038400 | yashsharma.vk@gmail.com | RQP3+9P Jaipur, Rajasthan | 225000 | 265000 |  |  |  | File login | Center (78K) | Loan apply | Project On Hold | Pending | [5 empty] | 0 | 0 | 0 | 0 | 0
7 | NAME UPDATE HOGA | TEAJA DEVI | 5KW |  | NAGAL BOHRA | SHALIMAR CHORHA | 210475007155 | 8619873804 | VINODSAIBI050489@GMAIL.COM | 26°58'36.7"N 75°44'47.2"E | 225000 | 270000 |  |  |  | File login | Center (78K) | Loan apply | Project On Hold | Pending | [5 empty] | 0 | 0 | 0 | 0 | 0

## SUNNY JI
NO | UPDATE | NAME | KW | PH | LOCATION | DISCOM | K.NO | MOBILE | GMAIL | GPS / LINK | QUATATION IN BANK | FINAL DEAL WITH CLIENT | DEAL WITH MSS | LOAN | CASH | FILE LOGIN | SUBSIDY | BANK FILE/CASH | WORK STATUS | DISCOM WORK | PAYMENT STATUS | 1ST INSTALLMENT | 2ND INATALLMENT | CASH TO MSS | PAYMENT WITH PARTNER | CASH DUE FROM CLIENT | BANK DUE | CASH DUE TO MSS | NET DUE TO MSS | TOTAL PAYMENT RECIVED | REMARK
1 | PRIVATE SE LOAN KRNA H | SANGITA DEVI | 6KW |  |  | SANGANER | 211463002618 | 99280 80167 | sunnymeema2003@gmail.com | RQCV+G7 Jaipur, Rajasthan | 390000 |  |  |  | 0 | File login | Both (78 + 17) | Loan Rejected | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | 0 | 0 | 0 | 0 | 0
2 | FILE LOGIN | MADHU KHURANA | 5KW | 3PH | SANGANER | SANGANER RURAL | 211584058090 | 9785643805 | KHURANARAILWAY@GMAIL.COM | 26°48'06.3"N 75°52'08.7"E | 260000 | 260000 | 165762 | 0 | 260000 | COMPLET | Both (78 + 17) | CASH FILE | I&C Completed | Subsidy apply with site photo | Cash To Mahi | 0 | 0 | 260000 |  | 0 | 0 | -94238 | -94238 | 260000

## DHERAJ JI SITES
NO | UPDATE | NAME | KW | PH | LOCATION | DISCOM | K.NO | MOBILE | GMAIL | GPS / LINK | QUATATION IN BANK | FINAL DEAL WITH CLIENT | DEAL WITH MSS | LOAN | CASH | FILE LOGIN | SUBSIDY | BANK FILE/CASH | WORK STATUS | DISCOM WORK | PAYMENT STATUS | 1ST INSTALLMENT | 2ND INATALLMENT | CASH TO MSS | PAYMENT WITH PARTNER | CASH DUE FROM CLIENT | BANK DUE | CASH DUE TO MSS | NET DUE TO MSS | TOTAL PAYMENT RECIVED | REMARK
1 | LOAN APPLY | RAMAVATRA KUMAWAT | 5KW | 1PH | MANDHA | RENWAL | 211544036585 | 9460871476 | DOULATKUMAWAT6@GMAIL.COM | 27°04'23.8"N 75°19'17.8"E | 225000 |  |  | 200000 | -200000 | File login | Center (78K) | File into bank | Work Not Started Yet | Pending | Payment Not Received Yet |  |  |  |  | -200000 | 200000 | -200000 | 0 | 0
Work Not Started Yet
Work Not Started Yet
Work Not Started Yet

## ALWAR SITES
No | UPDATE | Client | KW | LOCATION | DISCOM | K.NO | MOBILE | GMAIL | QUATATION in bank | FINAL DEAL | LOAN | LOCATION | File login | SUBSIDY | BANK FILE/CASH | WORK STATUS | DISCOM WORK | PAYMENT STATUS | PAYMENT TO US | 1ST INSTALLMENT | 2ND INSTALLMENT | TOTAL
1 | VENDOR REMOVE | RATAN LAL | 3KW |  |  | 210172021468 | 9116687990 | [5 empty] | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
2 | VENDOR REMOVE | RAJENDRA SINGH | 3KW | BHARATPUR | KUMBER | 211912010326 | 9460734745 | [5 empty] | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
3 | VENDOR REMOVE | PREMJIT | 3KW | BHARATPUR | KUMBER | 211912010317 | 9460310316 | [5 empty] | Doc Recieved | Both (78 + 17) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
4 | VENDOR REMOVE | RAJ KUMAR | 3KW | BHARATPUR | KUMBER | 211912042922 | 8561811748 | rajkumartam578@gmail.com |  |  |  |  | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
5 | CANCLE | UNESH KUMAR | 3KW |  |  |  | 9413787604 | choudharyunesh2@gmail.com |  |  |  |  | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
6 | CANCLE | JITENDRA CHOUDHARY | 3KW | ALWAR | LAXMANGARH | 210172034373 | 9783218887 | [5 empty] | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
7 | LOAN APPLY | AJAY SINGH | 3KW | ALWAR | KATHOOMAR | 210132015714 | 9982003851 | ajaysinghssb@gmail.com |  |  |  |  | File login | Both (78 + 17) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
8 | FILE LOGIN | TARESH SHARMA | 3KW | ALWAR | KATHOOMAR | 210132022443 | 7732852247 | tareshsharama@gmail.com |  |  |  |  | File login | Both (78 + 17) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
9 | FILE LOGIN | SHIV LAL | 3KW | ALWAR | KATHOOMAR | 210132017089 | 7073295214 | ANILJI0085@GMAIL.COM |  |  |  |  | File login | Both (78 + 17) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
10 | LOAN APPLY | SUJATA | 3KW | ALWAR | MIA | 210117029588 | 9694227425 | AJAY.ALWAR777@GMAIL.COM |  |  |  |  | File login | Both (78 + 17) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
11 | PAN NHI H | UDAI SINGH | 3KW | ALWAR | DEEG | 211911011092 | 8920644244 | [5 empty] | File login | Both (78 + 17) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
12 | FILE LOGIN | RAHUL KUMAR | 3KW | ALWAR | KATHOOMAR | 210132028641 | 7689810199 | RAHULRAJANA5@GMAIL.COM |  |  |  |  | File login | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
13 | FILE LOGIN | VIRENDRA SINGH | 3KW | ALWAR | LAXMANGARH | 210172021765 | 9772036747 | [5 empty] | File login | Both (78 + 17) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
14 | BANK NOT SHOW | NAVEEN | 3KW | ALWAR | LAXMANGARH | 210172037684 | 7689873281 | [5 empty] | File login | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
15 | FILE LOGIN | PRAHALA SINGH | 3KW | ALWAR | LAXMANGARH | 210172037685 | 6375622327 | [5 empty] | File login | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
16 | FILE LOGIN | MANOJ | 3KW | ALWAR | KATHOOMAR | 210132024207 | 7734044736 | CHOUDHARYMANOJ9535@GMAIL.COM |  |  |  |  | File login | Both (78 + 17) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
17 | FILE LOGIN | BHIM SINGH | 3KW | ALWAR | KATHOOMAR | 210132015841 | 8302785264 | sitaramrayana00@gmail.com |  |  |  |  | File login | Both (78 + 17) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
18 | FILE LOGIN | DEVO | 3KW | BHARATPURA | BRIJNAGAR | 211921049537 | 7339877186 | rp469603@gmil.com |  |  |  |  | File login | Both (78 + 17) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
19 |  | BHAGVAN SINGH | 3KW |  |  | 210261019912 | [6 empty] | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
20 |  | MUNESH DHAKAR | 3KW | [9 empty] | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
21 |  | OMVEER SINGH | 3KW |  |  | 210173020278 | 8290214187 | OMVERRSINGH61994@GMAIL.COM |  |  |  |  | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
22 |  | SEESRAM GURJAR | 3KW | ALWAR | KHERLI | 210131020572 | 98291 29403 | [5 empty] | Doc Recieved | Both (78 + 17) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
[13 empty] | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
[13 empty] | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
[13 empty] | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
[13 empty] | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
[13 empty] | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
[13 empty] | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
[13 empty] | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet
[13 empty] | Doc Recieved | Center (78K) | Loan apply | Project On Hold | Pending | Payment Not Received Yet

## summary
MSS
| NO.OF SITES | COMPLETED | REJECTED | IN PROGRESS | HOLD | DOC. ETC PENDING SITES | CASH FILE | METER PENDING
MSS | 34 | 8 | 1 | 11 | 3 | 8 | 3 | 8
ROHIT JI | 5 | 0 | 0 | 5 | 0 | 0 | 2
KAVITA JI | 8 | 1 | 1 | 1 | 0 | 5 | 0 | 1
SATANARYAN JI | 10 | 1 | 0 | 7 | 0 | 2 | 0 | 1
AJAY JI | 9 | 3 |  | 3 | 0 | 2 | 1
SUNNY | 2 | 0 | 0 | 0 | 0 | 1 | 1
ROHIT JI PHULERA | 1 | 0 | 0 | 1 | 0 | 0 | 0
ARKSHAKTI
| NO.OF SITES | COMPLETED | REJECTED | IN PROGRESS | HOLD | DOC. ETC PENDING SITES | CASH FILE
MSS | 34 | 27 | 2 | 3 |  | 2
ROHIT JI | 3 | 2 | 1 | 0 | 0 | 0 | 0
AJAY JI | 30 | 25 | 3 | 2